## TestScenarios
Project Name | Book House
Reference Document | FRS
Created By | Kawsar Newaz Chowdhury
Creation Date | 2025-03-06
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate the functionality of "Login" feature | P0 | 24
TS_002 |  | Validate the working of "Registration" feature | P0 | 12
TS_003 |  | Validate the "Logout" functionality | P0 | 2
TS_004 |  | Validate the working of "Forgotten Password?" functionality. | P0 | 10
TS_005 |  | Validate the funcitonality of "Shopping Cart" | P1 | 7
TS_006 |  | Validate the functionality of "Add to Wishlist" . | P3 | 4
TS_007 |  | Verify book details display correct informations. | P1 | 6
TS_008 |  | Validate the functionality of "Proceed to Checkout". | P2 | 2
TS_009 |  | Validate the functionality of " Payment Methodes" | P2
TS_010 |  | Verify that discount codes and promotions apply correctly. | P3
TS_011 |  | Validate the "Search & Filter or sorting" functionaity | P3 | 10
TS_012 |  | Validate the "Hotline" functionality | P4 | 5
TS_013 |  | Validate website compatibility across multiple browsers. | P0 | 1

## TestCase
Product Name |  | Book House | TC Start Date | 2025-03-06 | TC Execution Start Date | - - | [5 empty] | TEST CASE
Module Name |  |  | TC End Date |  | TC Execution End Date | - - |  |  |  |  | PASS | 73
Epic |  |  | Test Case Developed By | Kawsar Newaz Chowdhury | Browser (tested) | Yes |  |  |  |  | FAIL | 5
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | No |  |  |  |  | NO RUN | 7
Test Executed by | [10 empty] | BLOCKED | 1
[11 empty] | TOTAL | 86
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Account | Browser Compatibility Testing | Account | Checkinging by running the URL site in different browsers. | Should be run in different browsers. | Found as per expectation. | Browsers-Chrome, Mozilla Firefox, Brave. | 1. Go to different browsers. 3. Search 'https://bookhouse.com.bd/' . 3.Go to the website. |  |  | Passed
2 | User Authentication |  | Login | Verifying that the user will be able to log in with their account with the correct credential. | User should be able to login with correct credintial | Found as per expectation. |  | 1. Goto the URL https://bookhouse.com.bd/ 2. Click on the " Sign in" button in the right corner. 3.Enter correct credentials. 4. Click on " login" button |  |  | Passed
3 |  |  |  | Verifying all login-related elements and fields are present on the login page. | Should be present the all mandatory field | Found as per expectation. |  | 1. Goto the URL https://bookhouse.com.bd/ 2. Click on the "Login" button in the right corner. |  |  | Passed
4 |  |  |  | Verifying that the user will get into their dashboard screen after login in with the correct credentials. | User should be redirected to the dashboard after successful login. | Found as per expectation. |  | 1. Goto the URL https://bookhouse.com.bd/ 2. Click on the "Login" button in the right corner. 3. Enter correct credentials 4.Click on "login" button |  |  | Passed
5 |  |  |  | Verifying that the user can log in by entering valid credentials and presseing "Enter" key. | Should be able to log in successfully | Found as per expectation. |  | 1. Goto the URL https://bookhouse.com.bd/ 2. Click on the "Login" button in the right corner. 3. Enter correct credentials 4.Press "Enter" key |  |  | Passed
6 |  |  |  | Verifying that the user can log in by entering valid credentials and presseing "Login" button. | Should be able to log in successfully | Found as per expectation. |  | 1.Go to ' https://bookhouse.com.bd/ ' 2. Click on the "Login" button in the right corner. 3. Enter correct credentials 4.Click on "login" button |  |  | Passed
7 |  |  |  | Verifying that the password entered should be in encrypted form. | The password should be displayed in encrypted form while being entered. | Found as per expectation. |  | 1. Goto the URL https://bookhouse.com.bd/ 2. Click on the "Login" button in the right corner. 3. Enter correct password |  |  | Passed | dff
8 |  |  |  | Verifying whether an eye icon is added to the password field or not. | Eye-icon should be added to the password | Not found as per expectation. |  | 1. Goto the URL https://bookhouse.com.bd/ 2. Click on the "Login" button in the right corner. 3. Enter password | Eye Icon Screeshot |  | Failed | Eye icon missing
9 |  |  |  | Verifying the error message should display after just entering an email and leaving the password field blank. | An error message should be displayed after entering an email and leaving the password field blank. | Found as per expectation. |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the "Login" button in the right corner. 3. Enter correct email 4.Click on "login" button |  |  | Passed
10 |  |  |  | Verifying the error message should display after just entering the passowrd and leaving the email field blank. | An error message should be displayed after entering a password and leaving the email field blank. | Found as per expectation. |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the "Login" button in the right corner. 3. Enter correct password 4.Click on "login" button |  |  | Passed
11 |  |  |  | Verifying that error message should display after entering the invalid credentials. | The error message should display after just entering invalid credentials | Found as per expectation. |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the "Login" button in the right corner. 3. Enter invalid credentials 4.Click on "login" button |  |  | Passed
12 |  |  |  | Verifying that error message should display after entering an invalid email format. | The error message should display after entering an invalid email format | Found as per expectation. |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the "Login" button in the right corner. 3. Enter invalid email format 4.Click on "login" button |  |  | Passed
13 |  |  |  | Verifying logged-in user doesn’t log out by clicking the back button on the browser tab. | User should not logged out by clicking the back button on the browser tab | Found as per expectation. |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the "Login" button in the right corner. 3. Enter correct credentials 4.Click on "login" button 5. Redirect to Transaction page 6.Click on "Back" |  |  | Passed
14 |  |  |  | Verifying the displayed error message grammar should be correct. | The error message should be grammatically correct. | Found as per expectation. |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the "Login" button in the right corner. 3. Enter invalid credentials 4.Click on "login" button |  |  | Passed
15 |  |  |  | Verifying the displayed error message spell should be correct. | The spelling of error message should be correct. | Found as per expectation. |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the "Login" button in the right corner. 3. Enter invalid credentials 4.Click on "login" button |  |  | Passed
16 |  |  |  | Checking logged in user should not log out on closing the browser. | Browser should not be closed when new browser is openned | Found as per expectation. |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the "Login" button in the right corner. 3. Enter valid credentials 4.Click on "login" button 5. Close the browser 6. Goto the URL http://localhost:1337 |  |  | Passed
17 |  |  |  | Verifying the login screen will appear after clicking on a login link or login button. | The login screen should appear after clicking the login link or button. | Found as per expectation. |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the "Login" button in the right corner. |  |  | Passed
18 |  |  |  | Verifying that the login page of the application is responsive and aligns properly on different screen resolutions and devices. | The login page should be responsive and properly aligned on different screen resolutions and devices. | Found as per expectation. |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the "Login" button in the right corner. 3. Enter valid credentials 4.Click on "login" button 5. Right click on the mouse 6. Click on Inspect 7. Click toggle device toolbar 8. Checking with different device dimensions |  |  | Passed
19 |  |  |  | Verifying login page title. | The login page should display the correct title as per the application’s specifications. | Found as per expectation. |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the "Login" button in the right corner. |  |  | Passed
20 |  |  |  | Verifying if keyboard shortcut keys enable in the text area. Users can copy, cut or paste and select content on shift + Arrow Keys. | Keyboard shortcuts (copy, cut, paste, Shift + Arrow) should work in the text area. | Found as per expectation. |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the Login button in the right corner. 3. Paste/Copy/Cut an registered email 4. Click on Submit button |  |  | Passed
21 |  |  |  | Verifying that the text area is functional in case of any validation error message shown. | The text area should be functional during validation errors. | Found as per expectation. |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the Login button in the right corner. 3. Enter invalid email 4. Enter Password 5. Click on Submit button 6. Enter another email |  |  | Passed
22 |  |  |  | Verifying Backspace, delete keys should be functional | Backspace and Delete keys should be functional in the text area. | Found as per expectation |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the Login button in the right corner. 3. Enter a registered email 4.Enter Backspace/Delete key |  |  | Passed
23 |  |  |  | Verifying user can paste the copied content with keyboard keys Ctrl + v. | User should be able to paste copied content using Ctrl + V. | Functioning successfully |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the Login button in the right corner. 3. Press Ctrl+V at the email text field 4. Enter password 5. Click on Submit button |  |  | Passed
24 |  |  | Logout | Verify Successful Logout | User should be logged out successfully and redirected to the login page | Found as per expectation. |  | 1. Go to 'https://bookhouse.com.bd/ " 2. Click on the SignIn button in the right corner. 3. Click on login button and login with valid information 4. Click on the user name button in the right corner 5. Click on logout button |  |  | Passed
25 |  |  |  | Verify Logout Button Visibility | The "Logout" button should be clearly visible and accessible. | Found as per expectation. |  | 1. Go to 'https://bookhouse.com.bd/ " 2. Click on the SignIn button in the right corner. 3. Click on login button and login with valid information 4. Click on the user name button in the right corner |  |  | Passed
26
27 | User Registration |  | Register Account | Verifying by clicking on the "Register" button for blank input. | Clicking the "Register" button with blank input should show an error message. | Found as per expectation. |  | 1. Go to 'https://bookhouse.com.bd/ " 2. Click on the SignIn button in the right corner. 3. Click on Register button. 4. Click on the final Register button |  |  | Passed
28 |  |  |  | Verifying all fields related to registration present on the registration form. | All required fields should be present on the registration form. | Found as per expectation. |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the SignIn button in the right corner. 3. Click on Register button. |  |  | Passed
29 |  |  |  | Verifying password field should have validation for a minimum of 8 characters long. | Password field should validate at least 8 characters. | Found as per expectation. |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Hover on SignIn button and Click on the Register button in the right corner. 3. Enter password with length less than 8 4. Click Register button |  |  | Passed
30 |  |  |  | Verifying password added by the user should be protected, encrypted, and shown in (...). | The password should be encrypted and displayed as dots (…). | Found as per expectation |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Hover on SignIn button and Click on the Register button in the right corner. 3. Enter password with length 8 or more. |  |  | Passed
31 |  |  |  | Verifying whether the validation is added for the password and confirm whether passwords are the same or not. | Password validation should be applied, and the system should confirm if the passwords match. | Found as per expectation |  | 1. Go to 'https://bookhouse.com.bd/ ' 2. Hover on SignIn button and Click on the Register button in the right corner. 3. Enter password with lenght of 8 or more. 4. Re-enter password to confirm 5. Click Register button |  |  | Passed
32 |  |  |  | Verifying an eye icon added to the password and confirm the password field. | An eye icon should be present to toggle password visibility. | Not found as per expectation |  | 1. Go to 'https://bookhouse.com.bd/ ' 2. Hover on SignIn button and Click on the register button in the right corner. 3. Enter password with length of 8 or more. 4. Re-enter password to confirm 5. Click on Register button. | Icon Screenshot |  | Failed | Eye icon didn't found.
33 |  |  |  | Verifying that validation is added to the email field, only valid emails should be allowed to register successfully. | The email field should validate that only valid emails can be registered. | Found as per expectation |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Hover on SignIn button and Click on the Register button in the right corner. 3. Enter Invalid email 4. Enter password with length 8 or more. 5. Re-enter password to confirm 6. Click Register button |  |  | Passed
34 |  |  |  | Verifying that the user adds blank spaces and clicks on the register button an error message should be shown. | An error message should be shown. | Found as per expectation |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the SignIn button in the right corner. 3. Click on Register button. 4. Skip the email 5. Enter password with length 8 or more. 6. Re-enter password to confirm 7.Click Register button |  |  | Passed
35 |  |  |  | Verifying users can register successfully by entering valid credentials. | Users should be able to register successfully with valid credentials. | Found as per expectation |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the SignIn button in the right corner. 3. Click on Register button. 4. Enter valid email 5. Enter password with length 8 or more. 6. Re-enter password to confirm 7. Click Register button |  |  | Passed
36 |  |  |  | Test by trying to register with an already registered email address | Should not be able to register | Found as per expectation. |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the SignIn button in the right corner. 3. Click on Register button. 4. Enter email that is already used 5. Enter password with length 8 or more 6. Re-enter password to confirm 7. Click Register button |  |  | Passed
37 |  |  |  | Verifying the email verification link was sent to the user's email address successfully. | The email verification link should be sent to the user's email successfully. | Found as per expectation. |  | 1. Go to 'https://bookhouse.com.bd/ ' 2. Click on the SignIn button in the right corner. 3. Click on Register button. 4. Enter valid email 5. Enter password with length 8 or more 6. Re-enter password to confirm 7. Click Register button 8. Checking gmail inbox |  |  | Passed
38 |  |  |  | Verifying all spelling mistakes on the Register page. | Spelling should be correct. | Found as per expectation |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the SignIn button in the right corner. 3. Click on Register button. 4. Enter valid email 5. Enter password with length 8 or more 6. Re-enter password to confirm 7. Click Register button |  |  | Passed
39 | Password Reset |  | Forget password | Verifying that forget password link should be present on the login screen | Forgot Password" link should be visible and clickable on the login screen. | Found as per expectation |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the SignIn button in the right corner. |  |  | Passed
40 |  |  |  | Verifying that on clicking on the forget password link forget password page should open. | Clicking "Forgot Password" should open the password recovery page. | Found as per expectation |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the SignIn button in the right corner. 3. Click on Forgot Password button. |  |  | Passed
41 |  |  |  | Verifying that the email field is present on the forget password page to recover the password. | Email field should be present on the "Forgot Password" page. | Found as per expectation |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the SignIn button in the right corner. 3. Click on Forgot Password button. |  |  | Passed
42 |  |  |  | Verifying the whole button should be clickable not only the button text. | The entire button, not just the text, should be clickable. | Found as per expectation |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the SignIn button in the right corner. 3. Click on Forgot Password button. |  |  | Passed
43 |  |  |  | Verifying the displayed error message for unregistered should be meaningful. | Error message for unregistered users should be clear and informative. | Found as per expectation |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the SignIn button in the right corner. 3. Click on Forgot Password button. 4. Click on Resent password button |  |  | Passed
44 |  |  |  | Verifying the confirmation message check your email to recover the password should be displayed after clicking on the button by entering the registered email id. | A confirmation message should appear to check the email for password recovery. | Found as per expectation |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the SignIn button in the right corner. 3. Click on Forgot Password button. 4. Click on Resent password button |  |  | Passed
45 |  |  |  | Verifying that the user will get an email after entering a valid email id in forget password. | User should receive an email after entering a valid email ID in "Forgot Password." | Found as per expectation |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the SignIn button in the right corner. 3. Click on Forgot Password button. 4. Click on Resent password button |  |  | Passed
46 |  |  |  | Verifying the email which the user gets against forgot password should be displayed in the inbox, not in the spam folder. | The password recovery email should appear in the inbox, not the spam folder. | Found as per expectation |  | 1. Check register email inbox |  |  | Passed
47 |  |  |  | Verifying the user will get the forget password email from info@bookhouse.com.bd. | The password recovery email should be sent from info@bookhouse.com.bd. | Found as per expectation |  | 1. Check register email inbox |  |  | Passed
48 |  |  |  | Verifying the heading displayed in forget password screen should be ” Lost your password “ | The heading should be "Lost your password." | Found as per expectation |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Click on the SignIn button in the right corner. |  |  | Passed
49 | Search |  | Search Functionality | Verifying the search field is present and aligned. | The search field should be present and properly aligned on the page. | Found as per expectations |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Check Navbar for Search bar. |  |  | Passed
50 |  |  |  | Search for books by title. | Matching books should appear. | Found as per expectations |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Check Navbar for Search bar. 3. Enter book title in search bar. 4. Click Search |  |  | Passed
51 |  |  |  | Search for books by autor. | Books by that author should be listed. | Found as per expectations |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Check Navbar for Search bar. 3. Enter book author in search bar. 4. Click Search |  |  | Passed
52 |  |  |  | Search with invalid keywords. | "No results found" messege should appear. | Found as per expectations |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Check Navbar for Search bar. 3. Enter random keywords in search bar. 4. Click Search |  |  | Passed
53 |  |  |  | Search with special characters. | "No results found" messege should appear. | Found as per expectations |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Check Navbar for Search bar. 3. Enter special character in search bar. 4. Click Search |  |  | Passed
54 |  |  |  | Verify search with blank input. | Search results should display all books. | Found as per expectations |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Check Navbar for Search bar. 3. keep empty 4. Click Search |  |  | Passed
55 |  |  |  | Verify search functionality is case insensitive. | Matching books should appear. | Found as per expectations |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Check Navbar for Search bar. 3. Enter book title in lowercase or uppercase in search bar. 4. Click Search |  |  | Passed
56 |  |  |  | Checkinging if the user can paste the keyword with the mouse. | Can paste text that has been copied before | Found as per expectations |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Check Navbar for Search bar. 3. ight click on the mouse then paste book name in search bar. 4. Click Search |  |  | Passed
57 |  |  |  | Checkinging the search works on click on the search button. | Search will be appear | Found as per expectations |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Check Navbar for Search bar. 3. Enter book in search bar. 4. Click Search button |  |  | Passed
58 |  |  |  | Verifying the search works by pressing the Enter key on the keyboard. | Search will be appear. | Found as per expectations |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Check Navbar for Search bar. 3. Enter book name search bar. 4. Press the enter key on the keyboard |  |  | Passed
59 |  |  | Book Details | Verify that user can view book details. | Book details page should display information | Found as per expectations |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Scroll down for select a book. 3. Click on a book 4. Check book details |  |  | Passed
60 |  |  |  | Verify book cover image. | Book cover should be displayed | Found as per expectations |  | 1. Open book details page 2. Check if book cover is visible. |  |  | Passed
61 |  |  |  | Verify book description. | Description should be complete and formatted properly | Found as per expectations |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Scroll down for select a book. 3. Click on a book 4. Check book cover image |  |  | Passed
62 |  |  |  | Check related books section. | Relevant books should be displayed | Found as per expectations |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Scroll down for select a book. 3. Click on a book 4. Check book description |  |  | Passed
63 |  |  |  | Verify user reviews | User reviews should be displayed | Found as per expectations |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Scroll down for select a book. 3. Click on a book 4. Check book reviews |  |  | Passed
64 |  |  |  | Verify user ratings | User ratings should be visible. | Found as per expectations |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Scroll down for select a book. 3. Click on a book 4. Check book ratings |  |  | Passed
65 |  |  | Wishlist | Verify that user can add book to wishlist. | Book should appear in wishlist | Found as per expectations |  | 1. Go to ' https://bookhouse.com.bd/ ' 2. Scroll down for select a book. 3. Click on a book 4. Click on Wishlist |  |  | Passed
66 |  |  |  | Verify that user can remove book from wishlist | book should no longer be in wishlist | Found as per expectations |  | 1. Go to "https://bookhouse.com.bd/ 2. Click on wishlist button on the right corner of navbar 3. Click on remove button |  |  | Passed
67 |  |  |  | Verify wishlist persistence after logout | Wishlist should retain previously saved books | Found as per expectations |  | 1. Add book to wishlist 2. Loagout and log back 3. Check wishlist |  |  | Passed
68 |  |  |  | Verify wishlist limitation. | Proper memssage should appear if wishlist has a limitaiton | Not Found as per expectations |  | 1. Add multiple books to wishlist until limit is reached |  |  | Out of Scope | Didn't know the limitations while it's adding more and more books in wishlist
69 |  |  | Shopping Cart & Checkout | Verify that user can add book to cart. | Book should be in cart | Found as per expectations |  | 1. Go to "https://bookhouse.com.bd/" 2. Navigate to a book details page 3. Click "Add to Cart" 4. Navigate to Cart page |  |  | Passed
70 |  |  |  | Verify that user can remove book from cart. | Book should be removed from cart | Found as per expectations |  | 1. Go to "https://bookhouse.com.bd/ 2. Click on cart button on the right corner of navbar 3. Click on remove button |  |  | Passed
71 |  |  |  | Verify that cart updates totat price. | Taotal price should update accordingly | Found as per expectations |  | 1. Go to "https://bookhouse.com.bd/ 2. Add multiple books to cart 3. Check total price |  |  | Passed
72 |  |  |  | Verify user can proceed to checkout. | Order should be placed successfully | Found as per expectations |  | 1. Navigate to Cart page 2. Click "Checkout " 3. Enter shipping details. 4. Click "Place order" |  |  | Passed
73 |  |  |  | Verify empty cart message. | "Your cart is empty" message should be displayed | Not Found as per expectations |  | 1. Remove all books from cart 2. Check cart page | screenshot |  | Failed | No empty message displayed
74 |  |  |  | Verify book update quantity in cart. | Price should update based on quantity | Found as per expectations |  | 1. Navigate to Cart page 2. Increase or decrease quantity using "+" or "-" buttons 3. Verify total price update |  |  | Passed
75 |  |  |  | Verify out-of-stock message during checkout. | System should prevant checkout with an appropriate message. | Not Found as per expectations |  | 1. Add out-of-stock book to cart 2. Proceed to checkout | OutOfProduct OutOfProductOrder |  | Failed | checout proceed seccussfully
76 |  |  | Payment System | Verify complete payment with valid card. | Payment should be succeessful. |  |  | 1. Select credit cart option. 2. Enter valid card details 3. Click pay |  |  | Not Executed
77 |  |  |  | Verify attempt payment with invalid card | Payment should fail with error |  |  | 1. Enter incorrect card details. 2. Click pay |  |  | Not Executed
78 |  |  |  | Verify order confirmaion email. | Order confirmaion email should be reveived |  |  | 1. Complete order successfully 2. Check email inbox |  |  | Not Executed
79 |  |  |  | Verify Refund process | Refund should be processed sucessfully |  |  | 1. Request refund for a completed order. 2. Verify refund status. |  |  | Not Executed
80 |  |  |  | Verify test expired card payment. | Payment should be decline |  |  | 1. Enter expired card details. 2.Click pay |  |  | Not Executed
81 |  |  |  | Verify cash-on-delivery option | Order should be confirmed with COD option. |  |  | 1. Select " Cash on Delivery " during checkout 2. Place order. |  |  | Not Executed
82 |  |  |  | Verify saved payment methods | Payment method should be available for future use |  |  | 1. Add a new payment method 2. Save details. 3. Check if saved correctly. |  |  | Not Executed
83 |  |  |  | Verify that a valid contact number available in "Hotline" | A valid contact number should be available | Found as per expectation | none | 1. Go to "https://bookhouse.com.bd/" 2. Check for hotline nubmer in navbar |  |  | Passed
84 |  |  | Contact Us Functionality | Verifying user can initiate a "Contact Us" request via Facebook | Should able to send a direct message | Found as per expectation | none | 1. Goto to "https://bookhouse.com.bd/" 2. Scroll down to footer 3. Click facebook icon from contact us | FacebookPageNotFound |  | Failed | No facebook page or account found to send message.
85 |  |  |  | Verifying user can initiate a "Contact Us" request via Twitter. | Should able to send a direct message | Found as per expectation | none | 1. Goto to "https://bookhouse.com.bd/ " 2. Scroll down to footer 3. Click twitter icon from contact us |  |  | Passed
86 |  |  |  | Verifying user can initiate a "Contact Us" request via Instragram. | Should able to send a direct message | Found as per expectation | none | 1. Goto to "https://bookhouse.com.bd/ " 2. Scroll down to footer 3. Click Instragram icon from contact us |  |  | Passed
87 |  |  |  | Verifying user can initiate a "Contact Us" request via LinkedI | Should able to send a direct message | Found as per expectation | none | 1. Goto to "https://bookhouse.com.bd/ " 2. Scroll down to footer 3. Click Linkedin icon from contact us |  |  | Passed

## Test Summary Report
Test Case Report | [5 empty] | Result :
Project Name | Book House
Module Name | Account,User authentication,User registration |  |  |  |  | Total No. | Status | New Features:- | Testing Scope:-
Feature Name | Register Account ,Account Login,Book Order Functionality, Search Functionality
Test Case Version | 1 |  |  |  |  | 73 | PASS
Written By | Kawsar Newaz Chowdhury |  |  |  |  | 5 | FAIL
Executed By | Kawsar Newaz Chowdhury |  |  |  |  | 7 | Not Executed
Reviewed By | [5 empty] | 1 | Out of Scope
TEST EXECUTION REPORT
Testing Environment : Google Chrome Browser
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 73 | 5 | 7 | 1 | 86
Grand Total | 73 | 5 | 7 | 1 | 86
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
#SL 01
Issue: Eye-icon should be added to the password field when login
Reproducing Steps:
1. Goto the URL https://bookhouse.com.bd/
2. Click on the "Login" button in the right corner.
3. Enter email
4. Enter password
Env: Live website
Module: Login
Priority: P2
Severity: Minor
Screenshot:
Expected: Eye-icon should be added to the password
Responsible QA: Kawsar Newaz Chowdhury
Bug Reporting
#SL 02
Issue: Eye-icon should be added to the password field when login
Reproducing Steps:
1. Goto the URL https://bookhouse.com.bd/
2. Click on the "Registration" button in the right corner.
3. Enter email
4. Enter password
Env: Live website
Module: Registration
Priority: P2
Severity: Minor
Screenshot:
Expected: Eye-icon should be added to the password
Responsible QA: Kawsar Newaz Chowdhury
Bug Reporting
#SL 03
Issue:Verify empty cart message.
Reproducing Steps:
1. Goto the URL https://bookhouse.com.bd/
2. Remove all books from cart
3. Check cart page
Env: Live website
Module: Shopping Cart
Priority: P2
Severity: minor
Screenshot:
Expected: "Your cart is empty" message should be displayed
Responsible QA: Kawsar Newaz Chowdhury
Bug Reporting
#SL 04
Issue: Verify out-of-stock message during checkout.
Reproducing Steps:
1. Goto the URL https://bookhouse.com.bd/
2. Add out-of-stock book to cart
3. Proceed to checkout
Env: Live website
Module: Shopping Cart
Priority: P2
Severity: Minor
Screenshot:
Expected: System should prevant checkout with an appropriate message.
Responsible QA: Kawsar Newaz Chowdhury
Bug Reporting
#SL 05
Issue:Verifying user can initiate a "Contact Us" request via Facebook
Reproducing Steps:
1. Goto the URL https://bookhouse.com.bd/
2. Scroll down to footer
3. Click facebook icon from contact us
Env: Live website
Module: Contact Us
Priority: P1
Severity: Major
screenshot
Expected: Should able to send a direct message
Responsible QA: Kawsar Newaz Chowdhury

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (82/82)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/82)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (66/82)*100 = 80.5%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (16/82)*100 = 19.5%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/82)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A